## Sheet1
Risk Assessment/Matrix
| Negligible | Minor | Major | Hazardous | Catastrophic
Very Unlikely | Low | Low | Low Medium | Medium | Medium
Unlikely | Low | Low Medium | Low Medium | Medium | Medium High
Moderate | Low | Low Medium | Medium | Medium High | Medium High
Likely | Low | Low Medium | Medium | Medium High | High
Very Likely | Low Medium | Medium | Medium High | High | High
| Evaluation | Control Measures | Response | Likelihood | Impact | Responsibility | Risk Level
Applications VM goes down | Application goes offline | Use infrastructure as code to recreated machine and store in VCS | Recreate infrastructure on another machine | Very Unlikely | Catastrophic | AWS | Medium
Broken version deployed onto production | Deployed product may have issues or missing requirements | Automate tests before deployment and restrict access to pushing onto production branch | Revert back to a more stable version and build from there | Likely | High | Developers | Medium
RSI | Repetitively working in the same manner can put strain on wrist joints | Keep rotating wrists to ensure blood flow | Stay as comfortable as possible when working on laptop | Likely | Low | Developers | Low
Illness | Likelihood of getting illness e.g. Covid, Headaches | Stay safe and balanced nutrition | If illness severe enough to stop working, then seek medical advice from doctor or first aider. | Unlikely | Low | Developers | Low Medium
Loss of work | Computer restarting without control or software crashing before saving work | Save work regularly and have multiple versions in different locations | Use VCS and revert back to most recent version of work | Very unlikely | Hazardous | Developers | Medium
Knowledge gap | Not being in full knowledge prior to building virtual environment incorrectly configured security groups etc | Use Google and QA community to make sure I fill in gaps within my knowledge | Confirm current knowledge and utilise other resources available | Moderate | Minor | Developers | Low Medium
Internet cutting out | Internet cutting out and causing issue with building of virtual environment | Have access to wifi at another location to continue work if needed | Move to secondary location and continue from most recent saved work | Likely | Very Low | Internet Provider | Low Medium
Power outage | Power loss within the property | Charge laptop beforehand and hopefully power returns by time battery is in need of recharge | Ensure I can work in another location to not delay project at hand | Very unlikely | Hazardous | Power Company | Medium
Possibility of not meeting project deadline | Delayed project resulting in lower marks | Plan ahead and break down timeline with a well built JIRA board | Inform trainers and hope for an extension | Unlikely | Medium | Developers | Low
Possibility of someone in team sharing credentials | Database password resulting in unauthorised access to database | Only share credentials with those who this project is necessary and keep credentials as secure as possible | Inform trainers of situation and change credentials | Very Unlikely | Major | Developers | Medium
Unauthorised access to network | Unauthorised access could be used for malicious purposes e.g. taking down the app, stealing data, or setting blocks in network setup in order to cause technical issues. | Lock down access to VMs by locking down access to just IP of those actively working on the project | Inform trainers of situation and change credentials | Very Unlikely | Hazardous | Developers | Medium
Spill drink on keyboard/ hardware | This could result in damage to hardware necessary to work on the application. | Keep any liquids away from hardware and only access when required. | Dry hardware immediately and turn off other hardware connected in the process, if hardware is damaged then inform team and trainers to request backup. | Unlikely | Low | Developers | Low
Issues with adding csv files when using MySQL in EC2 | Results in us being unable to attach data to AWS RDS as user didn’t have correct permissions | Import data outside MySQL Server to avoid issues with permissions. | Import data outside MySQL Server to avoid issues with permissions and give permissions to AWS user to allow authorisation with MySQL. | Likely | Major | Developers | Low Medium
Team Member has planned leave | This may slow down the build of the application as less members at hand | Discuss any planned leave before project beigns, so that we can work around annual leave | Delegate work so that we can manage without an extra pair of hands and if anyone does get more time, they can help out | Likely | Low | Developers | Low
REFLECTION: One of the team member had issues with injury which caused a dealy in project afternoon of 27/09/21, however we had another member at hand that was also working on the same thing.
REFLECTION: One of the team member had loss of internet afternoon on the 29/09 which resulted in them only being able to do offline tasks, however this was managed as we had man power to cover.